## Operation Plan
OPERATION PLAN
Task | Responsible | Oct 10 | Oct 17 | Oct 24 | Oct 31 | Nov 7 | Nov 14 | Nov 21 | Nov 28 | Dec 5 | Dec 12 | Dec 19 | Dec 26
Preparation Stage
Conduct final market research and confirm pricing benchmarks for Terrace, BC. | Vivek Thakur | bar: Oct 10 to Oct 31
Finalize business name and register it provincially. | Vivek Thakur | bar: Oct 10 to Oct 31
Apply for a GST/HST number and register as a sole proprietorship in BC. | Vivek Thakur | bar: Oct 10 to Oct 31
Setup Stage
Open a dedicated business bank account | Vivek Thakur | bar: Nov 7 to Nov 14
Research and identify 2–3 reliable used cars to purchase. | Vivek Thakur | bar: Nov 7 to Nov 14
Operational Stage
Purchase vehicles, complete transfer and registration, and ensure each one passes BC safety inspection. | Vivek Thakur | bar: Nov 21 to Dec 12
Purchase required liability and commercial insurance. | Vivek Thakur | bar: Nov 21 to Dec 12
Complete vehicle maintenance (detailing, cleaning, any minor repairs). | Vivek Thakur | bar: Nov 21 to Dec 12
GPS trackers Install and digital key systems. | Vivek Thakur | bar: Nov 21 to Dec 12
Photograph vehicles for online listings | Vivek Thakur | bar: Nov 21 to Dec 12
Launch & Marketing Stage
Create Turo account, complete all host verification, set up PayPal account for payments, and list each car with optimized descriptions and competitive pricing. | Vivek Thakur | bar: Dec 19 to Dec 26
Set up digital channels (Google Business, Facebook, Instagram) | Vivek Thakur | bar: Dec 19 to Dec 26
Develop and schedule launch marketing: introductory promotions, initial ad spends, and outreach to local hotels, tourism agencies | Vivek Thakur | bar: Dec 19 to Dec 26
Ongoing: Monitor vehicle condition, customer satisfaction, and review financial performance weekly. Schedule car cleaning/maintenance after each booking; keep Turo response rate high